## Bugs
S.No | Bug ID | Module/Page | Bug Title | Severity | Priority | Steps to Reproduce | Expected Result | Actual Result | Browser/Device | Account Used | Screenshot/Video Link | Status | Assigned To | Reported By | Reported Date | Comments
1 | 001 | Sign Up | Signup Displays Server Error After Successful OTP Verification | Critical | High | 1. Launch the Browser. 2. Enter URL "https://app.saphercoin.com". 3. Click on Sign Up. 4. Enter Mobile Number. 5. Complete OTP Verification. 6. Enter Full Name and Email. 7. Click on "Create Account". | Account should be created successfully and user should be redirected to the dashboard | Application displays "Server Error" message after clicking Create Account | Chrome / Windows 11 | Test User Account | https://drive.google.com/file/d/1lLp2t7sHZI50qhqcuwnSz9i_XuT0mZel/view?usp=drive_link | Closed |  | Satyam sahu | 2026-06-04 | Issue was reproducible on 04-Jun-2026. During retesting on 05-Jun-2026, account creation completed successfully and no Server Error was observed.
2 | 002 | Wallet Dashboard / Transaction History | Wallet Address Remains Stuck in Infinite Loading State After Login | Critical | High | 1. Launch the Browser. 2. Enter the Url "https://app.saphercoin.com" 4. Enter mail-id and password. 5. Click on "Login". 6. Click on My wallet or My Transaction. 7. Observe Wallet Address section. | Wallet address should load successfully and be displayed to the user within a few seconds. | Wallet Address section remains stuck on "Loading..." indefinitely and the wallet address is not displayed. | Chrome / Windows 11 | Test User Account | https://drive.google.com/file/d/1pqFP4vrYJhr0LmkevDMfoWckcMKny9lf/view?usp=drive_link https://drive.google.com/file/d/1Dlfj8IpAcLm1V-3EeijRCOxKzpGEHKSG/view?usp=drive_link | Closed |  | Satyam sahu | 2026-06-04 | Issue was reproducible during initial testing and prevented wallet-related operations. During retesting, wallet address loaded successfully and issue could not be reproduced.
3 | 003 | Authentication / Network API Response | Sensitive Internal Configuration Information Exposed in API Response | Critical | High | 1. Launch the Browser. 2. Enter the URL "https://app.saphercoin.com". 3. Press F12 to open Developer Tools. 4. Navigate to the Network tab. 5. Login using valid credentials.. 6. Open the API responses returned after authentication. 7. Observe the response payload. | The API should return only the information required for frontend functionality. Internal system configuration, administrative information, and service configuration details should not be exposed to end users. | The API response exposes sensitive internal application information, including: * Administrative contact details * SMTP configuration details * OTP provider configuration * Payment gateway configuration * Internal tenant/project information * System configuration settings | Chrome / Windows 11 | Test User Account | https://drive.google.com/file/d/1L5gVTD3g-_K-Rl4qp7NsAYOARj5WfXzF/view?usp=drive_link | Open |  | Satyam sahu | 2026-06-05 | Sensitive internal configuration data is visible in browser network responses accessible to authenticated users. This information is not required for normal user operations and increases security exposure.
4 | 004 | Transaction History / Wallet | Incoming Transaction Not Showing in Receiver Transaction History | Medium | Medium | 1. Launch the Browser. 2. Enter the URL "https://app.saphercoin.com". 3. Login to user A Account. 4. Transfer coins to User B Account. 5. Verify the transfer is successful. 6. Logout as user A. 7. Login to User B Account. 8. click on Transaction History. 9. Refresh the page and login again. 10. Observe the user B history. | The incoming transaction should be displayed in the receiver's transaction history with the correct transaction details. | The receiver's balance is updated successfully, but the incoming transaction is not displayed in the transaction history. | Chrome / Windows 11 | Test User Account | https://drive.google.com/file/d/1nouTVRRsvRTIwJ25HVQuV_jzBeXNOOnC/view?usp=drive_link | Open |  | Satyam sahu | 2026-06-05 | Users cannot view or verify received transactions, resulting in incomplete transaction records.
5 | 005 | Dashboard - Sidebar Navigation | Sidebar Expand Button Is Partially Hidden After Collapsing Navigation Menu | Low | Medium | 1. Launch the Browser. 2. Enter the Url "https://app.saphercoin.com" 4. Enter mail-id and password. 5. Click on "Login" Button. 6. Collapse the left navigation menu. 7. Observe the expand button | The expand button should be fully visible and easily accessible to users. | The expand button is partially hidden behind the page content, making it difficult to notice and interact with. | Chrome / Windows 11 | Test User Account | https://drive.google.com/file/d/1Cfd20ECQ3ZEPdoIMtCEA-jCo75JG894_/view?usp=drive_link | Open |  | Satyam sahu | 2026-06-05
6 | 006 | Dashboard - Sidebar Navigation | Unnecessary Scrollbar Displayed in Sidebar After Collapsing Navigation Menu | Low | Low | 1. Launch the Browser. 2. Enter the Url "https://app.saphercoin.com" 4. Enter mail-id and password. 5. Click on "Login" Button. 6. Collapse the left navigation menu. 7. Observe the sidebar area | The sidebar should display all menu items properly without showing a scrollbar when the content fits within the available space. | A scrollbar appears inside the sidebar after collapsing the navigation menu, even though there is no additional content requiring scrolling. | Chrome / Windows 11 | Test User Account | https://drive.google.com/file/d/1vXeA2Ul1PAryjyRDFKjIqL454S7x2mVI/view?usp=drive_link | Open |  | Satyam sahu | 2026-06-05
7 | 007 | Sign Up / Profile | Name Fields Accept Special Characters and Excessively Long Input Without Validation | Medium | High | 1. Launch the Browser. 2. Enter the Url "https://app.saphercoin.com" 3. Click on Sign Up Link. 4. Enter Mobile Number. 5. Complete OTP Verification. 6. Enter special characters and an excessively long value in the Name field. Example: ssssssssssssssss@#$%^&*(){}[]?ssssssssssssssss 7. Enter Email. 8. Click on Signup. 9. Observe that user account got created successfully. | 1.Special characters should be restricted or validated. 2. Name fields should enforce a reasonable character limit. 3. Appropriate validation messages should be displayed for invalid input. | 1. The application accepts special characters in First Name and Last Name fields. 2. The application allows excessively long values without any character limit validation. 3. Invalid data is saved successfully and displayed on the Profile page. | Chrome / Windows 11 | Test User Account | https://drive.google.com/file/d/1NkzF1gG4i5DTIz5q-IoqdwxYcG_CIcer/view?usp=drive_link | Open |  | Satyam sahu | 2026-06-05 | Profile page displays names containing special characters and excessively long text entered during registration.
8 | 008 | Sign Up / Profile | Email Field Accepts Excessively Long Email Addresses Without Length Validation | Low | Low | 1. Launch the Browser. 2. Enter the Url "https://app.saphercoin.com" 3. Click on Sign Up Link. 4. Enter Mobile Number. 5. Complete OTP Verification. 6. Enter Full name. 7. Enter an excessively long email address. Example: ssssssssssssssssssssssssssssssssssssssssssssssssssssssssssssssssssssssssssssssssssssssssssssssssssssssssssssssssssss@gmail.com 8. Click on Signup. 9. Observe that user account got created successfully. | 1. The application should validate email length before account creation. 2. An appropriate validation message should be displayed when the allowed limit is exceeded. | 1. The application accepts excessively long email addresses without any length validation. 2. The email address is saved successfully and displayed in the Profile page. | Chrome / Windows 11 | Test User Account | https://drive.google.com/file/d/1moOwpyuoZEHd4JQqJ3TwFWgqlTf-s_lo/view?usp=drive_link | Open |  | Satyam sahu | 2026-06-05 | Invalid or unrealistic email data can be stored in the system, potentially causing data quality, display, and integration issues.
9 | 009 | Help & Support / All Tickets | Support Page Layout Breaks Horizontally Due to Lack of Text-Wrapping on Long Strings | Medium | High | 1. Launch the Browser. 2. Enter URL https://app.saphercoin.com. 3. Log in with valid credentials. 4. Navigate to Help & Support from the sidebar menu. 5. Click on All Tickets. 6. Observe the ticket display layout where an excessively long name/string (e.g., 2000+ characters without spaces) is rendered. | 1. The web page layout should remain responsive and fit within the screen bounds. 2. Long text strings should truncate gracefully using ellipses (...) to prevent layout distortion. 3. No unnecessary massive horizontal scrollbar should appear at the bottom of the page. | 1. The text container expands horizontally into infinity, completely breaking the UI alignment. 2. A massive horizontal scrollbar appears at the bottom of the page to accommodate the un-wrapped text. | Chrome / Windows 11 | Test User Account | https://drive.google.com/file/d/19tWDTHc3eA0PH1e9QRCtvrs8LMSVp1ta/view?usp=drive_link | Open |  | Satyam sahu | 2026-06-05 | The Help & Support page layout is completely broken because the UI lacks text-wrapping rules. Instead of moving to the next line, the long string expands horizontally into infinity, forcing a massive scrollbar at the bottom.
10 | 010 | Authentication / Omnichannel Login | Account Lockout: Absolute Authentication Failure (HTTP 400 / Server Errors) Across All Login Methods Due to Unsanitized, Over-sized Profile Name Payload | Critical | High | 1. Register a new user account or modify an existing profile to have a name string of 2000+ continuous characters without spaces. 2. Log out of the application. 3. Attempt to log back in using any available authentication method: a. Email Sign-in b. Mobile Number + OTP Verification c. login using Magic Link 4. Observe the page behavior and network response codes. | 1. The system should not allow an excessively long name string to be registered or saved in the first place, displaying a proper frontend validation error message. 2. The backend should successfully process the login without crashing or generating an oversized token that triggers an HTTP 400 Bad Request | The user is completely blocked from accessing the application. Every login gateway fails;throws an HTTP 400 Bad Request due to token header size limits, fail to process the corrupted profile payload, locking the user out indefinitely. | Chrome / Windows 11 | Test User Account | https://drive.google.com/file/d/1mv5tv078JWUs8lNirI4jL4KwrQwDWl8N/view?usp=drive_link | Open |  | Satyam sahu | 2026-06-05 | This is a high-priority blocker. If a malicious user or an accidental copy-paste inputs a massive string into their profile name, their account becomes permanently broken across all login options.
11 | 011 | Profile / Authentication (Reset Password vs Login) | Password Reset accepts blank spaces but subsequent Login fails due to input trimming mismatch | High | High | 1. Launch the Browser. 2. Enter the Url "https://app.saphercoin.com" 4. Enter mail-id and password. 5. Click on "Login" Button. 6. Click on Reset Password in the left navigation menu. 7. Log in and navigate to the Reset Password page. 8. Change the password to a string containing only spaces (e.g., " "). 9. use same password in confirm password field. 10. Observe that the password resets successfully without any validation error. 5. Log out of the application. 6. Try to log back in using the exact same password created in Step 8. | 1. Input Validation: The Reset Password field should not accept a password consisting entirely of blank spaces. 2. Consistency: If the system explicitly allows a password to be saved, it must allow the user to log in with that exact same input value. | The Login field password input does not accept spaces. causing completely locking the user out of their account. | Chrome / Windows 11 | Test User Account | https://drive.google.com/file/d/1pAg_4VkPhnvnEJWqbjdoKv2XLhwX_BM9/view?usp=sharing | Open |  | Satyam sahu | 2026-06-05 | Mismatch in string sanitization across processing boundaries. Login field strips input context, creating an authorization block.
12 | 012 | Wallet Dashboard | Transaction Amount field accepts extreme 200-digit decimal values without frontend validation or error warnings | Medium | High | 1. Launch the Browser. 2. Enter the Url "https://app.saphercoin.com" 4. Enter mail-id and password. 5. Click on "Login" Button. 6. Click on My wallet. 7. Enter valid address in the To Address Field. 8. In the "Amount" input field, type an extremely long decimal number (e.g., 1.2345... followed by 100 to 200 repeating characters/digits). 9. Observe if any real-time validation warning or character ceiling constraint appears. 10.click the "Send" button. | An explicit validation warning message should appear (e.g., "Invalid amount format" or "Maximum decimal limit exceeded"), and the "Send" button should be disabled. | 1. The input field allows the user to type arbitrary 200-digit long values with zero visual restrictions or errors. 2. Clicking "Send" successfully broadcasts the transaction instead of intercepting it as an invalid value at the UI layer. | Chrome / Windows 11 | Test User Account | https://drive.google.com/file/d/10-4i0ggP2HJH1aYBztxkTjY0ka3keMdy/view?usp=drive_link | Open |  | Satyam sahu | 2026-06-05 | Blockchain engine handles value safely via base unit truncation (dropping excess indices), but input lack represents a validation bug.
13 | 013 | Authentication | System allows concurrent active authentication sessions across multiple browser environments at the same time | Medium | Medium | 1. Launch the Browser. 2. Enter the Url "https://app.saphercoin.com" 4. Enter mail-id and password. 5. Click on "Login" Button. 6. Launch a new Browser in Different browser. 7. Login with same mail-id and password and click Login. 8. Click on My wallet. 9. Enter the address in the To Address Field in both browser. 10. Enter the amount in both browser. 11.click the "Send" button. | For a secure financial/wallet application, the system should enforce a single-session rule by either: 1. Automatically logging out/invalidating the session in the first browser window upon the second login. 2. Warning the user that an active session is already running from a different environment. | Both sessions remain fully active, authorized, and functional simultaneously. | Chrome / Windows 11 | Test User Account | https://drive.google.com/file/d/1gqdfoL_YJZUBPtc9ljJdDWPw3mm49nxm/view?usp=drive_link | Open |  | Satyam sahu | 2026-06-05 | During concurrent session testing, a secondary test was performed to trigger a double-spend transaction by transferring the same funds at the exact same time from both environments. The backend successfully blocked the second request due to insufficient funds, verifying that proper concurrency controls are enforced on the balance ledger.
14 | 014 | Logout | Clicking "Logout" does not actually close the session, allowing anyone to click the browser "Back" button and use the account | High | High | 1. Launch the Browser. 2. Enter the Url "https://app.saphercoin.com" 3. Enter mail-id and password. 4. Click on "Login" Button. 5. Click on My wallet. 6. Click the Logout button. 7. Once you are redirected to the login page, click the browser's Back arrow button 2-3 times. 8. Enter the address and amount. 9. Click on send. 10. Observer that transfer is successfully completed and also verified in public explorer. | The user should be completely logged out. Clicking the browser's "Back" button should either keep the user on the login screen or show an "unauthorized" error page, forcing them to log in again. | The application lets the user back into the dashboard. The account partially active, and anybody can still send money or see private data without entering a password. | Chrome / Windows 11 | Test User Account | https://drive.google.com/file/d/1zWZtX_u-0K2X2GhvBLy2iFP6p21DF-5W/view?usp=drive_link | Open |  | Satyam sahu | 2026-06-05 | This happens because the system only clears the screen when you click logout, but it forgets to delete the actual digital login key (token) from the browser memory.

## overview
Accounts | email | Wallet Address
7441115163 | ssahu7158@gmail.com | 0xe6708edb36f0c1be2a206bbcf648147a373386a3
9522139813 | ssahu7158@yahoo.com | 0x972Bf4a78cA90550F3Dc3D48BF03CecCe7F35288
872000398 | sssssssssssssssssssssssssssssssssssssssssssss@gmail.com | 0x8c65bc6c214160624fc75783f0d2bc7554d1de86
The Most Important Issues To Fix Right Away
Total Account Lockout (Bug 010): If a user types a very long name during sign-up, the system breaks. When they log out, they can never log back in via Gmail, OTP, or Magic Link because the login key becomes too heavy for the server to read.
Bypassing Logout via "Back" Button (Bug 014): When you click "Logout", the app looks like it logs you out, but it doesn't actually delete your security token. If you click the browser's Back arrow, you get right back into the wallet and can send money without logging in again.
Data Leak in API (Bug 003): The network backend is leaking secret internal codes, including corporate email passwords (SMTP) and payment gateway settings, to anyone who opens the browser's Developer Tools.